## TRANSITION TIMELINE
TITLE : RIC TRANSITION TIMELINE
TEAM LEAD: SOLOMON TSEAYO
MEMBERS: IBRAHIM TIJJANI
BASHIR SULEIMAN
RUKAIYA MUHAMMAD
LIU CHIKO
DURATION
PUBLIC HOLIDAYS
| START DATE: | 2020-08-04 |  |  |  | 1900-01-31 | [6 empty] | 1900-02-01 | [6 empty] | 1900-02-02 | [6 empty] | 1900-02-03
| WEEK OF | 1 |  |  |  | 2020-08-04 | [6 empty] | 2020-08-11 | [6 empty] | 2020-08-18 | [6 empty] | 2020-08-25
[6 empty] | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31
TASK | RESPONSIBLE | PROGRESS(%) | START DATE | END DATE | DURATION | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
FINANCIAL MANAGEMENT
Raise Budget | LIO | 100% | 2020-08-04 | 2020-08-07 | 3 Days
Determine amounts to be disbursed | DIR, LIO | 70% | 2020-08-10 | 2020-08-14 | 4 Days
Disbursement | DIR, LIO | 50%
Retirement | LIO, ACCT | 75%
MICROPLANNING |  | 80%
Target settlement list | M&E, LIO | 90%
Communicate with security personnel |  | 12%
Basic Excel skills used for the microplanning template |  | 5%
TRAINING OF IMPLEMENTING TEAMS |  | 35%
Vaccine administration and mangement | UNICEF,WHO | 100%
AFP surveillance | CDC,WHO
Use of Data tools | eHA
ADVOCACY AND FEEDBACK
verbal communication
Basic PowerPoint skills
TRACKING PROGRAM GOALS
Basic excel skills for RIC workbook management | M&E, LIO, DSNO
VACCINE ACCOUNTABILITY
Basic excel skills for accountability report
DEVELOP PROGRAM REPORTS
Basic Powerpoint skills
STAKEHOLDER MANAGEMENT
verbal communication
Basic Powerpoint skills
DATA MANAGEMENT
Basic Excel skills
Basic Powerpoint skills

## TRANSITION TIMELINE(all dataset (hidden)
PROJECT START DATE: | 2020-08-01
DISPLAY WEEK: | 1
[5 empty] | 2020-08-01 | [6 empty] | 2020-08-08 | [6 empty] | 2020-08-15 | [6 empty] | 2020-08-22
[5 empty] | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28
TASK | RESPONSIBLE | PROGRESS | START DATE | END DATE | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
FINANCIAL MANAGEMENT
Raise Budget |  |  | 2020-08-04 | 2020-08-09
Determine amounts to be disbursed |  |  | 2020-07-23
Disbursement
Retirement
Develop assessement tool
Method of training: 1hr lecture
Other resources(feasible?)
MICROPLANNING
Target settlement list
Communicate with security personnel
Basic Excel skills used for the microplanning template
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
TRAINING OF IMPLEMENTING TEAMS
Vaccine administration and mangement | UNICEF,WHO
AFP surveillance | CDC,WHO
Use of Data tools | eHA
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
ADVOCACY AND FEEDBACK
verbal communication
Basic PowerPoint skills
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
TRACKING PROGRAM GOALS
Basic excel skills for RIC workbook management | M&E, LIO, DSNO
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
VACCINE ACCOUNTABILITY
Basic excel skills for accountability report
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
DEVELOP PROGRAM REPORTS
Basic Powerpoint skills
Develop assessement tool |  |  | 2020-11-09 | 2020-11-13
Method of training: One-on-One mentorship
Other resources
STAKEHOLDER MANAGEMENT
verbal communication
Basic Powerpoint skills
Develop assessement tool
Method of training: One-on-One mentorship
Other resources
DATA MANAGEMENT
Basic Excel skills
Basic Powerpoint skills
Develop assessement tool
Method of training: One-on-One mentorship
Other resources

## HOLIDAYS (hidden)
Date |  | Name | Type | Details
2020-01-01 | Wednesday | New Year's Day | Public Holiday
2020-02-14 | Friday | Valentine's Day | Observance
2020-03-08 | Sunday | Women's Day | Observance
2020-03-20 | Friday | March Equinox | Season
2020-03-22 | Sunday | Mothering Sunday | Observance
2020-04-10 | Friday | Good Friday | Public Holiday
2020-04-11 | Saturday | Holy Saturday | Observance, Christian
2020-04-12 | Sunday | Easter Sunday | Observance, Christian
2020-04-13 | Monday | Easter Monday | Public Holiday
2020-05-01 | Friday | Workers' Day | Public Holiday
2020-05-24 | Sunday | Id el Fitr | Observance
2020-05-25 | Monday | Id el Fitr holiday | Public Holiday
2020-05-26 | Tuesday | Id el Fitr holiday | Public Holiday
2020-05-27 | Wednesday | Children's Day | Observance
2020-06-12 | Friday | Democracy Day | Public Holiday
2020-06-20 | Saturday | June Solstice | Season
2020-06-21 | Sunday | Father's Day | Observance
2020-07-31 | Friday | Id el Kabir | Public Holiday
2020-08-01 | Saturday | Id el Kabir additional holiday | Public Holiday
2020-08-02 | Sunday | Id el Kabir additional holiday | Public Holiday
2020-08-03 | Monday | Id el Kabir additional holiday | Public Holiday
2020-08-20 | Thursday | Al-Hijra | Local holiday
2020-09-22 | Tuesday | September Equinox | Season
2020-10-01 | Thursday | National Day | Public Holiday
2020-10-02 | Friday | National Day | Public Holiday
2020-10-29 | Thursday | Id el Maulud | Public Holiday
2020-10-30 | Friday | Id el Maulud | Public Holiday
2020-12-21 | Monday | December Solstice | Season
2020-12-22 | Tuesday | Sambisa Memorial Day | Local holiday | Borno
2020-12-24 | Thursday | Christmas Eve | Observance, Christian
2020-12-25 | Friday | Christmas Day | Public Holiday
2020-12-26 | Saturday | Boxing Day | Public Holiday
2020-12-31 | Thursday | New Year's Eve | Observance